## Sheet1
STUDY DESIGN | Preparing the study plan
Determine the study scope (geographical extent, duration).
Determine the available resources (budget, staff, equipment, supplies).
Determine how the data will be anlaysed (using a CABIN model or other methods).
Determine potential sampling locations with satellite tools (Google Earth or GIS).
Prepare sitecodes for potential sampling locations with estimated coordinates.
Prepare primary site information for potential sampling locations (basin, stream name, stream order, status).
FIELD LOGISTICS | Preparing field logistics
Confirm field crew availability.
Confirm field crew training.
Review field safety procedures and necessary PPE.
Develop a field sampling schedule and confirm appropriate timing (i.e. low flow, compatible with other regional CABIN data).
Gather CABIN equipment and supplies (refer to CABIN field manual Appendix 1).
If possible, confirm site status via site visit or reconnaissance (drive, boat, fly, hike).
Check water levels, weather, forest fire activity before departure.
SAMPLE ANALYSES | Preparing for analyses
Prepare for water quality analyses (contract, laboratory requirements for specific parameters, shipping, timing).
Prepare for taxonomic analyses (contract, sample management, shipping, vouchers, sample storage, data entry) (refer to CABIN lab manual, Appendix C).
Prepare for GIS analyses (contract or in-house, confirm coordinates for upstream delineations, confirm necessary data layers for required variables (i.e. CABIN model predictor variables), data entry).
CABIN DATABASE | CABIN Database and Analytical Tools
Request a CABIN study in CABIN database (title, purpose, description, authority).
Provide CABIN study access to team members as appropriate based on training (see below).
ÜData entry of field sheets and photos.
ÜData entry of taxonomy data from contract taxonomist (if not the taxonomist).
ÜData entry of water quality data from analytical laboratory.
ÜData entry of GIS data from GIS technician.
ÜData verification and validation (QA/QC).
ÜData analysis and reporting in CABIN.
ÜInterpret and report CABIN results.