## En- Year2 (hidden)
Two Year Rolling Risk Management Activities and Consultations Schedule [1]
June 2017
The following table provides a high level summary of risk management activities, including opportunities for stakeholder consultations and engagement, and is a source of information on risk management activities that are scheduled to occur during the next two years for substances managed under the Chemicals Management Plan. Note that the timelines of activities outlined in this table may be subject to change. The scope of activities included in this table relate to substances managed under the Chemicals Management Plan and does not include toxic substances under CEPA that are managed under other initiatives. This document is provided for information purposes only and is not an official set of commitments. It is not exhaustive and does not necessarily include all individual final instrument publications or instrument requirements. In the case of discrepancy between this document and the official instrument or regulations, the official version of the instrument or regulations prevails. Not all of the activities described in this table are intended for publication. For more detailed information on any of the activities outlined in the table, please refer to the relevant links in the table or contact eccc.substances.eccc@canada.ca.
Year 2
Risk Management Activity[2] | April 2017 - September 2017 | October 2017 - March 2018 | Instructions (will be deleted prior to publication) | Past items - please remove those completed or move to appropriate cell
Publication of Risk Management Scope document Initiation of consultations with stakeholders on preliminary risk management options | Risk Management Scope(s) where needed for draft CMP Phase 3 screening assessment reports. See Two-year Rolling Risk Assessment Publication Plan for the Third Phase of the CMP for more details on the publication schedule for risk assessments. | Risk Management Scope(s) where needed for draft CMP Phase 3 screening assessment reports. See Two-year Rolling Risk Assessment Publication Plan for the Third Phase of the CMP for more details on the publication schedule for risk assessments. | Scope of Contents to include RM Scopes scheduled to be published for all remaining CMP 1 (PSSA, Batch 12), CMP 2 substances, and all CMP 3 substances - with caveat "where needed". RA workplan will reference substance grouping names. | Risk Management Scope(s) where needed for assessments initiated prior to Phase 3 of CMP See Two-year Rolling Risk Assessment Publication Plan for the Third Phase of the CMP for more details on the publication schedule for risk assessments.
Publication of Risk Management Approach document Consultations on proposed risk management | Risk Management Approach(es) where needed for final assessments initiated prior to, and during Phase 3 of the CMP and other chemical substances of interest where needed See Two-year Rolling Risk Assessment Publication Plan for the Third Phase of the CMP for more details on the publication schedule for risk assessments. | Risk Management Approach(es) where needed for final assessments initiated prior to, and during Phase 3 of the CMP and other chemical substances of interest where needed See Two-year Rolling Risk Assessment Publication Plan for the Third Phase of the CMP for more details on the publication schedule for risk assessments. | Scope of Contents to include RM Approaches scheduled to be published for all remaining CMP 1 (PSSA, Batch 12), CMP 2 substances, and all CMP 3 substances - with caveat "where needed" Note - RA workplan will reference substance grouping names. | Risk Management Approach(es) where needed for final assessments initiated prior to Phase 3 of CMP See Two-year Rolling Risk Assessment Publication Plan for the Third Phase of the CMP for more details on the publication schedule for risk assessments.
Information Gathering including Monitoring and Surveillance to Support Risk Management* Information gathering activities may occur throughout the risk management process to support risk management decision-making and are done in addition to earlier information gathering activities to support risk assessment. *Notices under s.71 of CEPA may be issued following the publication of Risk Management Scope and/or Risk Management Approach documents as needed to support risk management decision-making | Study of The Typical Management and Disposal Practices of Wastewater Treatment Sludge in Canada and Impacts on Municipal Solid Waste Landfills | Study of Persistent Organic Pollutants in the Canadian Waste Sector | Information gathering includes but is not limited to monitoring & surveillance of toxic substances, voluntary information gathering activities, mandatory s.71 Notices, contract studies, and RM-related changes to NPRI thresholds. | Study of Current Activities Associated with the Use of DTBSBP (CAS RN 17540-75-9) in Brake Fluids in Canada Study of Sector Profile and Chemical Substances in the Plastic Recycling Sector in Canada Study of Landfill Cover Systems and Materials Used in Municipal Solid Waste Landfills in Canada Section 71 Notice with respect to certain substances informing the risk management of substances meeting or proposed to meet section 64 criteria of CEPA 1999
Consultations on risk management instrument development[3][4][5][6] Includes consultations on the design of instruments prior to publication in the Canada Gazette Pre-publication consultations seek input from stakeholders on the design of the proposed risk management instrument and typically occur 6 - 12 months prior to the publication of the proposed instrument. | Publication of a Consultation Document on the Proposed Pollution Prevention Planning Notice for Triclosan Pre-consultation on regulations to prohibit the manufacture and import of lead wheel weights in Canada Consultation on the Regulatory Approach to Prohibit Asbestos and Products that Contain Asbestos Consultations on the proposed regulatory approach for formaldehyde emissions from composite wood products. | Consultation Document on the Proposed Risk Management Instrument for DY3 | Includes consultations to inform publication of proposed instruments and tools (i.e. pre-CGI consultations). | Consultation on the working document for the Notice requiring the preparation and implementation of a pollution prevention plan for Reaction products of 2-propanone with diphenylamine (PREPOD) Pre-consulation on amendments to the Chromium Electroplating, Chromium Anodizing and Reverse Etching Regulations Consultation Document on the Options for Addressing Aromatic Azo and Benzidine-based Substances With Effects of Concern
Risk Management Instrument Publication Publication of proposed and final instruments (e.g. in Part I and II of the Canada Gazette ) Proposed regulatory initiatives under the CMP can be found in the Forward Regulatory Plan: https://www.ec.gc.ca/default.asp?lang=En&n=DF9C1A4C&offset=2&toc=show | Microbeads in Toiletries Regulations in Canada Gazette Part II Amendments to the Concentration of Phosphorus in Certain Cleaning Products Regulations in Canada Gazette Part I . Amendments to the Metal Mining Effluent Regulations (MMER) in Canada Gazette Part I Notice of Intent to amend the Significant New Activity provision for DEGME | * Regulations Amending the Prohibition of Certain Toxic Substances Regulations, 2012 (BNST) in Canada Gazette Part II * Amendments to the Chromium Electroplating, Chromium Anodizing and Reverse Etching Regulations - Public consultation in Canada Gazette Part I * Proposed Notice for the Pollution Prevention Plan of Reaction products of 2-propanone with diphynelamine (PREPOD) in Canada Gazette Part I * Proposed Regulations Repealing the Chlor-Alkali Mercury Release Regulations under CEPA * Proposed Regulations Repealing the Chlor-Alkali Mercury Liquid Effluent Regulations under the Fisheries Act * Amendments to the schedules of the Publication of proposed Notice requiring the preparation and implementation of pollution prevention plans in respect of TDIs in Canada Gazette Part I (final Notice will replace existing P2P Notice for foam sector) *Amendments to the Concentration of Phosphorus in Certain Cleaning Products Regulations in Canada Gazette Part I * Proposed Regulations to Prohibit the Manufacture and Import of Lead Wheel Weights in Canadain Canada Gazette Part I * Proposed Asbestos Prohibition Regulations in in Canada Gazette Part I | Includes CG I and CG II publications of proposed and final instruments and tools. Regulatory initiatives related to the CMP that are described in the Forward Regulatory Plan (FRP) should be included here and described using wording that is consistent with the FRP. | * Proposed Code of Practice for the environmentally sound management of end-of-life lamps containing mercury * Final Code of Practice for a Recommended Concentration of 2-(2-Methoxyethoxy) Ethanol (DEGME) in Surface Coating Materials Available to Consumers in Canada - publication in Canada Gazette Part I * Proposed Regulations Amending the Prohibition of Certain Toxic Substances Regulations, 2012 (BNST) - publication in Part 1 of the Canada Gazette * Regulations Repealing the Vinyl Chloride Release Regulations, 1992 * Regulations Amending the Prohibition of Certain Toxic Substances Regulations, 2012 (HBCD, PFOA, LC-PFCAs, PBDEs, PFOS) in Canada Gazette Part II * Proposed Environmental Emergency Regulations, 2016 - publication in Canada Gazette Part I * Proposed Regulations Addressing Petroleum and Refinery Gases - publication in Canada Gazette Part 1 * Proposed Microbeads in Toiletries Regulations - publication in Canada Gazette Part I. * Notice requiring the preparation and implementation of pollution prevention plans in respect of hydrazine related to the electricity sector
Risk Management Instrument Implementation Key implementation milestones of instruments including reporting, and compliance promotion activities | Environmental Performance Agreement Respecting Bisphenol A in Paper Recycling Mill Effluents - Final Report was due in November 2016. ECCC will publish a report on the final year in the period. ECCC will publish on its website a progress report for the Pollution Prevention Planning Notice for Base Metals Smelters and Refineries and Zinc Plants, including progress in reducing emissions of mercury and other metals Final report on progress made under the Environmental Performance Agreement Respecting Perfluorocaboxylic Acids (PFCAs) and their Precursors in Perfluorinated Products Sold in Canada will be published (http://www.ec.gc.ca/epe-epa/default.asp?lang=En&n=AE06B51E-1) | EC will publish on its website a report of progress made under the Environmental Performance Agreement 2015-2020 - Respecting the Use of Tin Stabilizers in the Vinyl Industry | Publication timelines including key milestones where relevant such as coming into effect dates and reporting deadlines. | * Products Containing Mercury Regulations, product reporting by March 31, 2017. (http://ec.gc.ca/lcpe-cepa/eng/regulations/detailReg.cfm?intReg=203) * Environmental Performance Agreement Respecting Perfluorocaboxylic Acids (PFCAs) and their Precursors in Perfluorinated Products Sold in Canada - Last Report Due in October 2016 (http://www.ec.gc.ca/epe-epa/default.asp?lang=En&n=AE06B51E-1) * Prohibition of Certain Toxic Substances Regulations, 2012 -application for BNST permit renewals for last year of permitted use under Regulations (permit valid from March 14, 2017 to March 13, 2018) * ECCC will publish on its website a report of progress made under the Environmental Performance Agreement 2015-2020 - Respecting the Use of Tin Stabilizers in the Vinyl Industry
Performance Measurement Evaluation of risk management actions including performance measurement of instruments and broad performance measurement initiatives such as substance-based performance measurement. | With respect to EPA respecting Bisphenol A in Paper Recycling Mill Effluents, the final report will include an evaluation of the performance of the instrument. Note that ECCC did not specify in the EPA when the report would be released. It could potentially be delayed to fiscal year 2019-20 as this activity is unfunded. | Performance Report: Notice Requiring the Preparation and Implementation of Pollution Prevention Plans in Respect of Cyclotetrasiloxane, octamethyl- (Siloxane D4) in Industrial Effluents - based on Schedule 5 - Preliminary report Performance Report on the Environmental Performance Agreement respecting Refractory Ceramic Fibre - Fall 2017 January 2018 | Publication of Instrument-based performance measurement results and substance-based performance measurement results. | Performance Report: Notice Requiring the Preparation and Implementation of Pollution Prevention Plans in Respect of Cyclotetrasiloxane, octamethyl- (Siloxane D4) in Industrial Effluents - based on Schedule 4 - Preliminary report Performance Report – Pollution Prevention Planning Notice for the Polyurethane and Other Foam Sector (except Polystyrene) in Respect of Toluene Diisocyanates (TDIs) - based on Schedule 5 Performance Report: Environmental Performance Agreement Respecting Perfluorocaboxylic Acids (PFCAs) and their Precursors in Perfluorinated Products Sold in Canada - Publication of ECCC report on final results reporting on 2015 commitment (http://www.ec.gc.ca/epe-epa/default.asp?lang=En&n=AE06B51E-1 )
International Risk Management Activities Canada's involvement in international risk management activities support Canada's domestic risk management objectives. | ECCC Strategy on Enhancing Engagement in the Multilateral Environmental Agreements - status report on progress, consultations and documents (e.g. Final Strategy Released). Outcomes of the 2017 Conferences of the Parties (COP) to the Stockholm, Rotterdam and Basel Conventions (post-COP webinar and reports at relevant venues, as appropriate). Outcomes of Minamata Convention COP-1, anticipated to be held in September 2017 (highlights will be provided at relevant venues, as appropriate) | Preparations for Minamata Convention COP-2 (engagement at relevant venues, as appropriate) Share highlights of intersessional activities of the Conferences of the Parties to the chemicals Multilateral Environmental Agreements, including anticipated substances for listing, issues of relevance to CMP (as appropriate/if applicable). Commission for Environmental Cooperation (CEC) and Bilateral files - Report on results of Phase II of CEC migration project. | Meetings on MEAs, domestic consultations to inform Canada'a participation in international activities. Scope of activities to include activities under GLBTS, Stockholm, and other international activities that relate to CMP substances. | ECCC Strategy on Enhancing Engagement in the Multilateral Environmental Agreements - status report on progress, consultations and documents (e.g. draft Strategy and implementation plan) for input and advice Commission for Environmental Cooperation (CEC) - Report on results of Phase I of CEC migration project Preparations for the back-to-back meetings of the 2017 Conferences of the Parties (COP) to the Stockholm, Rotterdam and Basel Conventions (details on pre-COP webinar and presentations at relevant venues, as appropriate) Preparations for Minamata Convention COP-1 (engagement at relevant venues, as appropriate)
1 Abbreviations: CEPA: Canadian Environmental Protection Act, 1999; CMP: Chemicals Management Plan; ECCC: Environment and Climate Change Canada; CEC : Commission for Environmental Cooperation; COP : Conferences of the Parties, PNUE : Programme des Nations Unies pour l'environnement; UNEA: United Nations Environment Assembly
2 Additional information on risk management activities may be found in the Chemicals Management Plan Progress Report, which reports on advances in major initiatives and highlights key activities related to the Government of Canada's recent work under the CMP [http://chemicalsubstanceschimiques.gc.ca/plan/progress_report-rapport_etape-eng.php]
3 For more information on public consultations that are currently in progress under CEPA, refer to the Public Consultations webpage on the CEPA Environmental Registry: http://ec.gc.ca/lcpe-cepa/eng/participation/
4 For more information on Health Canada's consultations on Existing Substances, refer to: http://www.hc-sc.gc.ca/ewh-semt/consult/index-eng.php#exist
5 For more information on the full range of current consultation activities at Environment and Climate Change Canada, as well as links to public engagement opportunities from other government departments and agencies, refer to: http://www.ec.gc.ca/consultation/
6 For more information on Government of Canada public consultations, refer to: http://www1.canada.ca/consultingcanadians/

## En- Year4
Two Year Rolling Risk Management Activities and Consultations Schedule [a]
The following table provides a high level summary of risk management activities, including opportunities for stakeholder consultations and engagement, and is a source of information on risk management activities that are scheduled to occur during the next two years for substances managed under the Chemicals Management Plan. Note that the timelines of activities outlined in this table may be subject to change. The scope of activities included in this table relate to substances managed under the Chemicals Management Plan and does not include toxic substances under CEPA that are managed under other initiatives. This document is provided for information purposes only and is not an official set of commitments. It is not exhaustive and does not necessarily include all individual final instrument publications or instrument requirements. In the case of discrepancy between this document and the official instrument or regulations, the official version of the instrument or regulations prevails. Not all of the activities described in this table are intended for publication. For more detailed information on any of the activities outlined in the table, please refer to the relevant links in the table or contact eccc.substances.eccc@canada.ca.
Year 4
Risk Management Activity[b] | April 2019 - September 2019 | October 2019 - March 2020
Publication of Risk Management Scope document Initiation of consultations with stakeholders on preliminary risk management options | Risk Management Scope(s) where needed for draft CMP Phase 3 screening assessment reports. See Two-year Rolling Risk Assessment Publication Plan for the Third Phase of the CMP for more details on the publication schedule for risk assessments. | Risk Management Scope(s) where needed for draft CMP Phase 3 screening assessment reports. See Two-year Rolling Risk Assessment Publication Plan for the Third Phase of the CMP for more details on the publication schedule for risk assessments.
Publication of Risk Management Approach document Consultations on proposed risk management | Risk Management Approach(es) where needed for final assessments initiated prior to, and during Phase 3 of the CMP and other chemical substances of interest where needed See Two-year Rolling Risk Assessment Publication Plan for the Third Phase of the CMP for more details on the publication schedule for risk assessments. | Risk Management Approach(es) where needed for final assessments initiated prior to, and during Phase 3 of the CMP and other chemical substances of interest where needed See Two-year Rolling Risk Assessment Publication Plan for the Third Phase of the CMP for more details on the publication schedule for risk assessments.
Information Gathering including Monitoring and Surveillance to Support Risk Management* Information gathering activities may occur throughout the risk management process to support risk management decision-making and are done in addition to earlier information gathering activities to support risk assessment. *Notices under s.71 of CEPA may be issued following the publication of Risk Management Scope and/or Risk Management Approach documents as needed to support risk management decision-making | - | -
Consultations on risk management instrument development[c][d][e][f] Includes consultations on the design of instruments prior to publication in the Canada Gazette Pre-publication consultations seek input from stakeholders on the design of the proposed risk management instrument and typically occur 6 - 12 months prior to the publication of the proposed instrument. | Second public consultation on a proposed approach for managing oil sands mining effluent releases. | Consultation on risk management instrument for BENPAT
Risk Management Instrument Publication Publication of proposed and final instruments (e.g. in Canada Gazette Part I and II) Proposed regulatory initiatives under the CMP can be found in the Forward Regulatory Plan: https://www.ec.gc.ca/default.asp?lang=En&n=DF9C1A4C&offset=2&toc=show | Publication of the Final Pollution Prevention Plan Notice for PREPOD in CG1 Publication of the proposed Federal Halocarbon Regulations in Canada Gazette Part I Publication of proposed regulations amending the Ozone-depleting Substances and Halocarbon Alternatives Regulations in Canada Gazette Part I Publication of the proposed Regulations Amending the Chromium Electroplating, Chromium Anodizing and Reverse Etching Regulations in Canada Gazette Part I (phase 2); Publication of the proposed amendments for the Products Containing Mercury Regulations in CGI. Publication of the proposed Code of Practice for MDIs Publication of the proposed Formaldehyde Emissions from Composite Wood Products Regulations in Canada Gazette, Part I Publication of the Regulations Repealing the Chlor-Alkali Mercury Release Regulations in CGII. | Proposed Coal Mining Effluent Regulations in Canada Gazette Part I Proposed Amendments to the Prohibition of Certain Toxic Substances Regulations (HBCD, PBDEs, PFOS, PFOA, LC-PFCAs, DP, DBDPE) in Canada Gazette Part I. Publication of the proposed amendments for the Products Containing Mercury Regulations in Canada Gazette Part I; Publication of the proposed Lead Wheel Weight Regulations in Canada Gazette Part I. Publication of the proposed Regulations Amending the Chromium Electroplating, Chromium Anodizing and Reverse Etching Regulations in Canada Gazette Part I (phase 2); Publication of the final Regulations Amending the Chromium Electroplating, Chromium Anodizing and Reverse Etching Regulations in Canada Gazette Part II (phase 1); Publication of the final Regulations Respecting Reduction in the Release of Volatile Organic Compounds (Petroleum Sector) Publication of the final release guidelines for DY3 and 25 other azo dyes in Canada Gazette Part I; Publication of the renewal Environmental Performance Agreement 2020-2025 Respecting the Use of Tin Stabilizers in the Vinyl Industry and the revised Guideline for the Environmental Management of Tin Stabilizers in Canada Publication of the proposed Code of Practice to Minimize Releases of Chemicals into the Environment from the Chemicals, Plastics and Rubber Sectors in Canada Gazette Part I
Risk Management Instrument Implementation Key implementation milestones of instruments including reporting, and compliance promotion activities | ECCC will publish on its website reports of progress made under the Environmental Performance Agreements 2018-2025 for the base metals smelters and aluminium and alumina sectors, and 2018-2026 for the iron ore pellet sector. Publication of a Progress Report concerning the Environmental Performance Agreement 2015-2020 - Respecting the Use of Tin Stabilizers in the Vinyl Industry. Proactive compliance promotion activities will be delivered on the following: - Chromium Electroplating, Chromium Anodizing and Reverse Etching Regulations - Concentration of Phosphorus in Certain Cleaning Products Regulations - Environmental Emergency Regulations - Export and Import of Hazardous Waste and Hazardous Recyclable Material Regulations - Microbeads in Toiletries Regulations - New Substances Notification Regulations (Organisms) - PCB Regulations - Products Containing Mercury Regulations - Prohibition of Asbestos and Products Containing Asbestos Regulations - Prohibition of Certain Toxic Substances Regulations, 2012 - Storage Tank Systems for Petroleum Products and Allied Petroleum Products Regulations - Tetrachloroethylene (Use in Dry Cleaning and Reporting Requirements Regulations). Publication of a progress report concerning the Environmental Performance Agreement (2015-2020) Respecting the Use of Tin Stabilizers in the Vinyl Industry Publication of the third progress report on the Code of Practice for the Management of Tetrabutyltin in Canada Launch of the new online reporting tool for the Environmental Emergency regulations, 2019. Webinars relating to the new Environmental Emergency Regulations (E2R), 2019 and the new online reporting system in order to assist industry in meeting regulatory requirements. Development of compliance promotion tools related to E2R. Numerous compliance promotion activities related to E2R all across Canada. | ECCC will publish on its website a report of progress made under the 2006 Pollution Prevention Planning Notice for base metals smelters and refineries and zinc plants. Webinars relating to the new Environmental Emergency Regulations (E2R), 2019 and the new online reporting system in order to assist industry in meeting regulatory requirements. Numerous compliance promotion activities related to E2R all across Canada.
Performance Measurement Evaluation of risk management actions including performance measurement of instruments and broad performance measurement initiatives such as substance-based performance measurement. | Final report concerning the completion of the P2P Notice for isoprene | Publication of a Performance Measurement Strategy to establish a long-term approach to systematically assessing the effectiveness of actions taken by the Government of Canada to manage risks from toxic substances. ECCC plans to publish a substance based performance evaluation on the ecological risk management actions for BPA, which will outline and measure the progress made towards meeting the environmental and risk management objectives. Jointly with HC, ECCC plans to publish substance based performance evaluations for mercury and for lead.
International Risk Management Activities Canada's involvement in international risk management activities support Canada's domestic risk management objectives. | - | -
a Abbreviations: CEPA: Canadian Environmental Protection Act, 1999; CMP: Chemicals Management Plan; ECCC: Environment and Climate Change Canada; CEC : Commission for Environmental Cooperation; COP : Conferences of the Parties, PNUE : Programme des Nations Unies pour l'environnement; UNEA: United Nations Environment Assembly
b Additional information on risk management activities may be found in the Chemicals Management Plan Progress Report, which reports on advances in major initiatives and highlights key activities related to the Government of Canada's recent work under the CMP https://www.canada.ca/en/health-canada/services/chemical-substances/chemicals-management-plan/progress-report.html
c For more information on public consultations that are currently in progress under CEPA, refer to the Public Consultations webpage on the CEPA Environmental Registry: https://pollution-waste.canada.ca/environmental-protection-registry/active-consultations
d For more information on Health Canada's consultations on Existing Substances, refer to: https://www.canada.ca/en/health-canada/services/environmental-workplace-health/consultations.html#exist
e For more information on the full range of current consultation activities at Environment and Climate Change Canada, as well as links to public engagement opportunities from other government departments and agencies, refer to: https://www.canada.ca/en/environment-climate-change/corporate/transparency/consultations.html
f For more information on Government of Canada public consultations, refer to: https://www.canada.ca/en/government/system/consultations/consultingcanadians.html

## En- Year5
Two Year Rolling Risk Management Activities and Consultations Schedule [a]
The following table provides a high level summary of risk management activities, including opportunities for stakeholder consultations and engagement, and is a source of information on risk management activities that are scheduled to occur during the next two years for substances managed under the Chemicals Management Plan. Note that the timelines of activities outlined in this table may be subject to change. The scope of activities included in this table relate to substances managed under the Chemicals Management Plan and does not include toxic substances under CEPA that are managed under other initiatives. This document is provided for information purposes only and is not an official set of commitments. It is not exhaustive and does not necessarily include all individual final instrument publications or instrument requirements. In the case of discrepancy between this document and the official instrument or regulations, the official version of the instrument or regulations prevails. Not all of the activities described in this table are intended for publication. For more detailed information on any of the activities outlined in the table, please refer to the relevant links in the table or contact eccc.substances.eccc@canada.ca.
Year 5
Risk Management Activity[b] | April 2020 - September 2020 | October 2020 - March 2021
Publication of Risk Management Scope document Initiation of consultations with stakeholders on preliminary risk management options | Risk Management Scope(s) where needed for draft CMP Phase 3 screening assessment reports. See Two-year Rolling Risk Assessment Publication Plan for the Third Phase of the CMP for more details on the publication schedule for risk assessments. | Risk Management Scope(s) where needed for draft CMP Phase 3 screening assessment reports. See Two-year Rolling Risk Assessment Publication Plan for the Third Phase of the CMP for more details on the publication schedule for risk assessments.
Publication of Risk Management Approach document Consultations on proposed risk management | Risk Management Approach(es) where needed for final assessments initiated prior to, and during Phase 3 of the CMP and other chemical substances of interest where needed See Two-year Rolling Risk Assessment Publication Plan for the Third Phase of the CMP for more details on the publication schedule for risk assessments. | Risk Management Approach(es) where needed for final assessments initiated prior to, and during Phase 3 of the CMP and other chemical substances of interest where needed See Two-year Rolling Risk Assessment Publication Plan for the Third Phase of the CMP for more details on the publication schedule for risk assessments.
Information Gathering including Monitoring and Surveillance to Support Risk Management* Information gathering activities may occur throughout the risk management process to support risk management decision-making and are done in addition to earlier information gathering activities to support risk assessment. *Notices under s.71 of CEPA may be issued following the publication of Risk Management Scope and/or Risk Management Approach documents as needed to support risk management decision-making | - | -
Consultations on risk management instrument development[c][d][e][f] Includes consultations on the design of instruments prior to publication in the Canada Gazette Pre-publication consultations seek input from stakeholders on the design of the proposed risk management instrument and typically occur 6 - 12 months prior to the publication of the proposed instrument. | Consultations on the proposed risk management intruments for Natural Gas Condensates (NGCs). Public consultation on the proposed risk management instrument for chlorhexidine and its salts. | -
Risk Management Instrument Publication Publication of proposed and final instruments (e.g. in Canada Gazette Part I and II) Proposed regulatory initiatives under the CMP can be found in the Forward Regulatory Plan: https://www.ec.gc.ca/default.asp?lang=En&n=DF9C1A4C&offset=2&toc=show | - | Final Amendments to the Prohibition of Certain Toxic Substances Regulations (HBCD, PBDEs, PFOS, PFOA, LC-PFCAs, DP, DBDPE) in Canada Gazette Part II. Publication of the final Code of Practice to Minimize Releases of Chemicals into the Environment from the Chemicals, Plastics and Rubber Sectors in Canada Gazette Part I
Risk Management Instrument Implementation Key implementation milestones of instruments including reporting, and compliance promotion activities | Compliance promotion activities for 2020-21 will be determined during 2019-20, based on need/priority of increasing awareness of the risk management instruments. Numerous compliance promotion activities related to E2R all across Canada. | Compliance promotion activities for 2020-21 will be determined during 2019-20, based on need/priority of increasing awareness of the risk management instruments. Numerous compliance promotion activities related to E2R all across Canada.
Performance Measurement Evaluation of risk management actions including performance measurement of instruments and broad performance measurement initiatives such as substance-based performance measurement. | Publication of the final report concerning the Environmental Performance Agreement (2015-2020) Respecting the Use of Tin Stabilizers in the Vinyl Industry | -
International Risk Management Activities Canada's involvement in international risk management activities support Canada's domestic risk management objectives. | Environmental Emergency Prevention group to start looking into modernizing the Environemntal Emergency Regulations, 2019 to a "class-based" model instead of being product based. | Environmental Emergency Prevention group to start looking into modernizing the Environemntal Emergency Regulations, 2019 to a "class-based" model instead of being product based.
a Abbreviations: CEPA: Canadian Environmental Protection Act, 1999; CMP: Chemicals Management Plan; ECCC: Environment and Climate Change Canada; CEC : Commission for Environmental Cooperation; COP : Conferences of the Parties, PNUE : Programme des Nations Unies pour l'environnement; UNEA: United Nations Environment Assembly
b Additional information on risk management activities may be found in the Chemicals Management Plan Progress Report, which reports on advances in major initiatives and highlights key activities related to the Government of Canada's recent work under the CMP https://www.canada.ca/en/health-canada/services/chemical-substances/chemicals-management-plan/progress-report.html
c For more information on public consultations that are currently in progress under CEPA, refer to the Public Consultations webpage on the CEPA Environmental Registry: https://pollution-waste.canada.ca/environmental-protection-registry/active-consultations
d For more information on Health Canada's consultations on Existing Substances, refer to: https://www.canada.ca/en/health-canada/services/environmental-workplace-health/consultations.html#exist
e For more information on the full range of current consultation activities at Environment and Climate Change Canada, as well as links to public engagement opportunities from other government departments and agencies, refer to: https://www.canada.ca/en/environment-climate-change/corporate/transparency/consultations.html
f For more information on Government of Canada public consultations, refer to: https://www.canada.ca/en/government/system/consultations/consultingcanadians.html